## Sheet1
Task No | Task | Status | Progress | Start date | End date | Assignees
1 | Clinical Evaluation report | In Progress | 50 | 2025-06-05 | 2025-06-11 | Aishwarrya
2 | Software update as per Clinical trial | In Progress | 75 | 2025-06-12 | 2025-06-13 | Aishwarrya
3 | R&D Testing and trouble shooting | In Progress | 60 | 2025-06-16 | 2025-06-17 | Aishwarrya,Mohit,Shajiya
4 | V&V Testing | In Progress |  | 2025-06-18 | 2025-06-19 | Verification,Rajiv Sharma
5 | PED trail and testing | In Progress | 80 | 2025-06-20 | 2025-06-25 | PED,Rajiv Sharma
6 | Production trial and QA Testing | In Progress | 100 | 2025-06-20 | 2025-06-30 | Production,Rajiv Sharma
7 | IMPACT analysis meeting | In Progress | 100 | 2025-06-05 | 2025-06-09 | QARA,PED,PMO,R&D,Verification
8 | ECN Closer | In Progress | 100 | 2025-06-10 | 2025-06-13 | QARA,R&D