## updateddata
Task No | Task | Status | Progress | Start date | End date | Assignees | Remarks
1 | Multi Export to be added from C View II to C View FD | Not Started | 0 | 2025-06-01 | 2025-06-10 | Aishwarrya VP;Vrinda Bhat | Dependecy issue, less information
2 | Pan bug - Export screen | Completed | 100 | 2025-04-08 | 2025-10-15 | Thakarkuldip;Aishwarrya VP;Vrinda Bhat
3 | Remove FPS and drop down and Add Speed | Hold | 25 | 2025-04-30 | 2025-10-27 | Vrinda Bhat
4 | Clean Cview FD code, remove the warnings | Hold | 75 | 2025-01-13 | 2025-08-27 | Thakarkuldip;Vrinda Bhat
5 | Setup Code structure for release and Debug configuration | In Progress | 50 | 2025-05-02 | 2025-08-19 | Thakarkuldip
6 | R&D for SharpScan (Image quality check software) | In Progress | 25 | 2025-03-22 | 2025-07-25 | Thakarkuldip
7 | Checking FFT transform for image with different filter , to resolve grid lines issue | Completed | 100 | 2025-04-20 | 2025-08-14 | Thakarkuldip
8 | Set default x64 release architecture for Cview-FD code. | Completed | 50 | 2025-05-22 | 2025-08-09 | Aishwarrya VP
9 | Merge all the changes to one final updated code | Completed | 100 | 2025-03-15 | 2025-09-01 | Vrinda Bhat
10 | Dynamically change the UI of the Splash screen | In Progress | 25 | 2025-05-13 | 2025-07-11 | Vrinda Bhat
11 | Enable and Disable buttons during Exposure | In Progress | 50 | 2025-02-14 | 2025-09-06 | Vrinda Bhat
12 | Offset status bar | In Progress | 25 | 2025-02-19 | 2025-06-29 | Vrinda Bhat
13 | Hardware Settings - Save clicked - closes application | In Progress | 75 | 2025-01-08 | 2025-06-30 | Aishwarrya VP;Vrinda Bhat
14 | Worklist gets hanged - during reconnection | In Progress | 50 | 2025-04-11 | 2025-07-09 | Vrinda Bhat
15 | Add to Ref button - added in Recall Section | In Progress | 25 | 2025-01-15 | 2025-10-28 | Vrinda Bhat
16 | Collect Multiple good and bad images to train model For R&D | Not Started | 0 | 2025-02-10 | 2025-11-19 | Thakarkuldip
17 | Collect images and write Custom algorithm to Enhance the image quality | In Progress | 25 | 2025-01-13 | 2025-09-17 | Thakarkuldip
18 | Explore about DSA to implement for Cview FD | Completed | 100 | 2025-01-18 | 2025-11-15 | Thakarkuldip
19 | Start implementing OPENCV in the current code to optimize and increase speed. | In plan | 25 | 2025-05-30 | 2025-06-20 | Thakarkuldip
20 | Find a suitable way to reduce the time taken for software initialization. | Not Started | 0 | 2025-01-04 | 2025-10-03 | Aishwarrya VP;Vrinda Bhat
21 | Get DSA Code of XMED from Niha's PC | Completed | 100 | 2025-03-11 | 2025-08-22 | Aishwarrya VP
22 | Reframe the requirements of C VIEW-FD | In Progress | 25 | 2025-05-16 | 2025-10-04 | Aishwarrya VP;Thakarkuldip
23 | Make the new SRS for CVIEW-FD | Not Started | 0 | 2025-07-21 | 2025-08-23 | Aishwarrya VP
24 | Submit the SRS | Not Started | 0 | 2025-07-22 | 2025-08-24 | Thakarkuldip
25 | Get approval | Not Started | 0 | 2025-07-23 | 2025-08-25 | Thakarkuldip